## Sheet1
ID | Priority | Area | Feature | Owner | Description | Status | last status date | version last tested
11 | 2 | Backend | API for recording logged actions | Joaz | Custom module for voting (thumbs up and down) | open | 2014-03-25 | 2
6 | 2 | Android Client | thumb up and thumb down | Chen | thumb up and thumb down is recorded to the backend | open | 2014-03-25 | 2
9 | 1 | Android Client | back arrow to channels | Chen | clicking the arrow above left of the video allows the user to go back to the channel guide | fixed | 2014-03-25 | 2
8 | 1 | android Client | back and forward | Chen | plays the previous video and the next video | testing | 2014-03-25 | 2
10 | 1 | android Client | pause | Chen | pressing the play button again allows the user to pause the video | fixed | 2014-03-25 | 2
4 | 1 | android Client | thumbnails | Chen | load thumbnails for next videos | testing | 2014-03-25 | 2
5 | 1 | android Client | skip video | Chen | if the user clicks thumbs down, go to next video | fixed | 2014-03-25 | 2
1 | 2 | android Client | misspelling | Kurt | Misspelling on the word 'Developed' | open | 2014-03-25 | 2
13 | 1 | backend | remove bad URLs | Joaz | enable the removal of bad urls from the drupal manager | open | 2014-03-25 | 2
14 | 2 | backend | upload video | backend dev | investigate whether we can upload hi-def videos for prototype and streaming to the App in addition to URLs from Youtube | open | 2014-03-25 | 2
15 | 1 | AWS | analyze the usage of AWS | backend dev | Limit the spend per month until launch | open | 2014-04-02 | 2
16 | 1 | content | define the appropriate bitrate and resolution for videos | Kurt | define the ideal video content bitrate and resolutions to maximize experience and save money | open | 2014-04-02 | 2
17 | 2 | content | integrate music service with video | backend dev | API to be determined... | on hold
18 | 1 | setup | github and AWS | Joaz | setup github and repositories for Android and Drupal | in progress | 2014-04-09 | 2
19 | 2 | backend | registration | Evi | registration for users - e2e - facebook or email | open | 2014-04-11 | 2
20 | 1 | drupal | update drupal | Joaz | update with latest security patch | open | 2014-04-16 | 2
21 | 1 | Setup Drupal |  | joaz | a) Features, for have sync DB options with others in the team based on site features and enabled via code.¦¦b) Drupal services, to enable a web services API server to serve the content via REST, XMLRPC, JSON, JSON-RPC, SOAP, AMF. ¦¦c) oAuth to make a better and secure Authentication in both, web and app. ¦¦ d) Creation and setup of taxonomy terms to works as the main channels video data. | in progress | 2014-04-26 | 2
22 | 1 | deployment |  | joaz | 1 - Setup varnish - APC (we need decide which one to use, I recommend varnish) to cache the Drupal content and settings.¦¦2 - Python script to deploys from github repository to ASW dev server¦¦3 - Python script to after a deploy, send an email with the DB_dump of the last deploy (for cases when the DB was updated). | in progress | 2014-04-26 | 2
23 | 1 | media |  | joaz | 1 - Media, Internet Media, and Youtube Media are modules implemented in the first version.¦¦2 - Views, jQuery_update, Display Suite and Field Format to enable some content screens for admins (to see channels, filter content, search content, see videos).¦¦3 - Drupal vote API and Rate Module to handle the videos, this offer sync with Services API to handle with the mobile app the options to retrieve the users thumbs_up/down in the videos. | in progress | 2014-04-26 | 2